## Overview
PROJECT PLAN & PAYMENT SCHEDULE
Custom Export Management System ¦ Jaikvin Global, Mumbai
Prepared for | Jaikvin Global — Merchant Exporter, Mumbai
Scope | End-to-end export management system (6-stage workflow)
Total project value | ₹1,80,000
Planned duration | 45–60 working days (scheduled at ~50)
Start date | Friday, 26 June 2026
Target go-live | Thursday, 03 September 2026
Approach | Prototype-first, then phased development
Revisions | R1 & R2 on the prototype; R3, R4 & R5 across the build
Payments | 30% advance · 20% after R2 · 20% after R3 · 30% before go-live
Issued | 26 June 2026
How this works: We show you a working prototype first (R1), refine it (R2), then build the system in three phases. After each phase you review it and your changes are carried into the next phase — so no time is lost. After R5 only final changes are made; then we deploy.

## Project Schedule
PROJECT SCHEDULE
Stage | Review | What we will deliver | Days | Target date | Payment due | Status | Date
Kickoff | — | Project kicks off. 30% advance received to begin work. | — | Fri 26 Jun 2026 | 30% advance | Pending
Prototype — Build | R1 | Working prototype of the core flow: buyer order intake (2A), supplier packing receipt with automatic FIFO deduction (7A), and the live FIFO balance register. You see the system end-to-end. | 4 | Thu 02 Jul 2026 | —
Prototype — Finalize | R2 | Your R1 feedback implemented over one week. Finalized prototype presented for sign-off — this locks the look, flow and scope before the real build starts. | 5 | Thu 09 Jul 2026 | 20% | Pending
Phase 1 — Core System | R3 | The engine: database & data model from your 2A and 7A masters, buyer order intake, supplier packing receipt with FIFO deduction, and FIFO balance registers tracking pending quantities across buyer POs. | 15 | Thu 30 Jul 2026 | 20% | Pending
Phase 2 — Documentation | R4 | Pre-shipment documents (invoice, packing list, etc.) and post-shipment documents (BL and related) generated automatically from order & packing data. R3 changes implemented in parallel. | 10 | Thu 13 Aug 2026 | —
Phase 3 — Reports & Banking | R5 | Reports module and banking module (realization, RoDTEP, etc.), plus data-consistency checks that catch mismatches like the package-count and net-weight differences found in your files. R4 changes implemented in parallel; final changes collected. | 10 | Thu 27 Aug 2026 | 30% | Pending
Stage | Review | What we will deliver | Days | Target date | Payment due | Status | Date
Kickoff | — | Project kicks off. 30% advance received to begin work. | — | Fri 26 Jun 2027 | 30% advance | Pending

## Revision Schedule
REVISION SCHEDULE
Revision | What you review | Target date | What happens next
R1 | Working prototype (core flow) | Thu 02 Jul 2026 | You give feedback; we make changes over the next week.
R2 | Finalized prototype | Thu 09 Jul 2026 | You sign off; development begins.
R3 | Phase 1 — Core System | Thu 30 Jul 2026 | Your changes are folded into Phase 2.
R4 | Phase 2 — Documentation | Thu 13 Aug 2026 | Your changes are folded into Phase 3.
R5 | Phase 3 — Reports & Banking | Thu 27 Aug 2026 | Final changes only — then we deploy. No revisions after this.

## Payment Schedule
PAYMENT SCHEDULE
Total project value |  | 180000
# | Payment trigger | On / before | Share | Amount | Cumulative
1 | Advance — before R1 (project kickoff) | Fri 26 Jun 2026 | 30% | 54000 | 54000
2 | After R2 — finalized prototype signed off | Thu 09 Jul 2026 | 20% | 36000 | 90000
3 | After R3 — Phase 1 (Core System) signed off | Thu 30 Jul 2026 | 20% | 36000 | 126000
4 | After R5 — before deployment | Thu 27 Aug 2026 | 30% | 54000 | 180000
TOTAL |  |  | 100% | 180000
Note: amounts update automatically if the total project value cell (highlighted) is changed. All figures in Indian Rupees (₹). Milestone dates are targets and may shift slightly with feedback turnaround.